AESS Board of Governors Meeting, September 2012

Status update for 2013 International Conference on Radar Systems

Dr. Joe Fabrizio

AESS Board of Governors

International Director for Australia and New Zealand

1	Date of conference

The conference will be held from Monday 9 – Thursday 12 September 2013.

2	Venue

- Quotes were gained from a number of venues in Adelaide from hotel style to Convention centre.

- The Hotel Grand Chancellor Adelaide on Hindley was chosen.

- This decision was based on a significantly lower price, however service and style is of a good 4 star standard.

- It is a centrally located hotel in the CBD of Adelaide with close access to a range of other accommodation venues (in price and style).

- A small number of rooms at alternative accommodation venues, such as apartments, have been booked.

3	Theme

The theme for the conference is:

Beyond Orthodoxy: New Paradigms in Radar

Much of the progress in radar science, technology and applications follows a path of evolutionary development, but every so often we encounter a revolutionary advance in some supporting technology, or a novel idea which changes the way we think about radar and how it can be exploited. Radar 2013 welcomes contributions in all areas of radar science and engineering, but particularly encourages papers which open exciting new avenues for exploration and force us to embrace new paradigms.

4	Program Outline

See Appendix A for a program outline.

- In summary the program overview is:

Monday 9 September

Tutorials

Welcome Reception

Tuesday 10 September

Keynote and concurrent sessions

Wednesday 11 September

Keynote and concurrent sessions

Conference Dinner

Thursday 12 September

Keynote and concurrent sessions

5	Budget

- A draft budget has been prepared with 3 scenarios of 200, 250 and 300 delegates.

- Registration fees are as follows:

| Earlybird Member Registration | $750.00 |
| --- | --- |
| Earlybird Non-Member Registration | $875.00 |
| Standard Member Registration | $850.00 |
| Standard Non-Member Registration | $975.00 |
| Student/Discounted Registration | $400.00 |
| Day Member Registration | $410.00 |
| Day Non-Member Registration | $450.00 |
| Student Day Registration | $250.00 |

- The sponsorship and exhibition target is $52,500.

- With the above amounts, and known and estimated expenditure, the breakeven figure is currently 175 paying delegates.

6	Keynote Speakers

- A comprehensive list of potential keynote speakers has been developed. 6-8 speakers are currently being shortlisted with invitations then to be issued.

- A mixture of Australian and international speakers will be chosen with an aim to include a speaker form the Asia-Pacific region.

7	Tutorials

- There is the potential to hold eight tutorials.

- Six have been confirmed so far (as listed below), with invitations for another 2 being issued.

  - Inverse problems in radar (Stuart Anderson)

  - OTH radars (Joe Fabrizio)

  - Foliage penetration radar – FOPEN (Mark Davis)

  - Introduction to ISAR (Marco Martorella)

  - Radar imaging – SAR processing (Fabrizio Berizzi)

  - STAP Techniques (Brahma Himed)

  - Tutorials will only proceed if minimum numbers are reached as they must cover costs.

8	Call for Abstracts

- The call for abstracts is currently being prepared (at the time of this report being prepared on 3/8/12), with the view of releasing in September 2012.

- A number of subthemes have been developed to guide the submissions and create streams of concurrent sessions.

9	Sponsorship and Exhibition

- A sponsorship prospectus has been developed with a range of sponsorship packages, and an exhibition component.

- This is currently being distributed to a database developed by the committee.

10	Social program

- Welcome Reception

  - The reception is to be held onsite at the conference venue on the evening of Monday 9 September.

  - This will be held amongst the exhibition providing additional exposure.

  - The cost is inclusive with full registration.

- Conference Dinner

  - The dinner will be held on the evening of Wednesday 10 September.

  - A decision at the next meeting is expected as to the location to the dinner.

  - The choices are either the conference venue or the National Wine Centre. The National Wine Centre is a short distance form the CBD, and would require coach transfers. It is a unique venue in Adelaide highlighting local produce, specifically the wine of South Australia.

  - The cost of the dinner is inclusive with full registration.

11	Website

- A conference website has been developed detailing the major components of the conference and is to be used as the main source of information for delegates.

- www.radar2013.org.au

12	Marketing

- Networks and databases via IEEE and Engineers Australia will be used to publicise the conference.

- Engineers Australia will send three e-blast to members on key dates – call for abstracts announcement, 2 weeks prior to close of early bird date, and 2 weeks prior to the conference.

- A LinkedIn event page has been set up and will be regularly updated announcing key information.

- The website will be a major tool in providing current information about the conference.

Appendix A

Draft program

| Monday 9 September |
| --- |
| 7.00am-3.00pm- | Exhibitor build and bump-in Torrens Room 2 &3 |
| 9.00am-5.00pm | Workshops (4 in am and 4 in pm) |
| 3.00pm-6.00pm | Registration Foyer |
| 6.00pm-8.00pm | Welcome Reception Foyer |
| Tuesday 10 September |
| 8.00am-5.00pm | Registration Foyer |
| 9.00am-9.15am | Official Welcome & Welcome to Delegates Ballroom |
| 9.15am-10.00am | Plenary – Keynote Speaker Ballroom |
| 10.00am-10.45am | Plenary – Keynote Speaker Ballroom |
| 10.45am-11.15am | Morning Tea Foyer |
| 11.15am-12.45pm | Concurrent Session 1 Hindley 1 | Concurrent Session 2 Hindley 2 | Concurrent Session 3 Hindley 3 |
| 12.45pm-1.45pm | Lunch Foyer |
| 1.45pm-3.15pm | Concurrent Session 1 Hindley 1 | Concurrent Session 2 Hindley 2 | Concurrent Session 3 Hindley 3 |
| 3.15pm-4.15pm | Afternoon Tea Foyer |
| 4.15pm-5.15pm | Concurrent Session 1 Hindley 1 | Concurrent Session 2 Hindley 2 | Concurrent Session 3 Hindley 3 |
| Wednesday 11 September |
| 8.30am | Registration Foyer |
| 9.00am-9.45am | Plenary - Keynote Speaker Ballroom |
| 9.45am-10.30am | Plenary - Keynote Speaker Ballroom |
| 10.30am-11.00am | Morning Tea Foyer |
| 11.00am-12.30pm | Concurrent Session 1 Hindley 1 | Concurrent Session 2 Hindley 2 | Concurrent Session 3 Hindley 3 |
| 12.30pm-1.30pm | Lunch Foyer |
| 1.30pm-3.00pm | Concurrent Session 1 Hindley 1 | Concurrent Session 2 Hindley 2 | Concurrent Session 3 Hindley 3 |
| 3.00pm-3.30pm | Afternoon Tea Foyer |
| 3.30pm-5.00pm | Concurrent Session 1 Hindley 1 | Concurrent Session 2 Hindley 2 | Concurrent Session 3 Hindley 3 |
| 7.00pm-11.00pm | Conference Dinner Ballroom, Grand Chancellor |
| Thursday 12 September |
| 8.30am-1.00pm | Registration Foyer |
| 9.00am-9.45am | Plenary - Keynote Speaker Ballroom |
| 9.45am-10.30am | Plenary - Keynote Speaker Ballroom |
| 10.30am-11.00am | Morning Tea Foyer |
| 11.00am-12.30pm | Concurrent Session 1 Hindley 1 | Concurrent Session 2 Hindley 2 | Concurrent Session 3 Hindley 3 |
| 12.30pm-1.30pm | Lunch Foyer |
| 1.30pm-3.00pm | Concurrent Session 1 Hindley 1 | Concurrent Session 2 Hindley 2 | Concurrent Session 3 Hindley 3 |
| 3.00pm-3.30pm | Afternoon Tea Foyer |
| 3.30pm-5.00pm | Concurrent Session 1 Hindley 1 | Concurrent Session 2 Hindley 2 | Concurrent Session 3 Hindley 3 |